## Sheet1
Executive Management
Allocate Site Staff including project manager and site team
Administration & Special Procedures
Obtain Building Permit and Affectation Plan
NOC from Relevant Authority
Apply for demarcation and obtain accurate building lines/benchmark from Municipality
Apply and obtain approval from authorities for Temporary electricity if applicable
Arrange for generators
Apply and obtain approval from authorities for Temporary water meter if applicable
Arrange for water tanks and plumbing work
Apply and obtain temporary telephone, fax, and internet lines
Collect Municipality drawings
Complete all procedures to activate project insurances
Project Management
Prepare Mobilization plan and circulate copies of the Programme
Prepare Method Statement for project mobilization
Apply for temporary site fencing permit.
Construct site fencing
Provide Client, Contractor, Consultant site offices
Supply and erect Project Identification (sign boards)
Provide mess facility for Labour,
Toilet block, and ablution block, including septic tank
Provide Equipment Schedule the site facility requirements for load
Obtain Performance Bond (if applicable)
Submit Obtain Advance Payment Guarantee (if applicable)
Submit site staff CVs to the Client/Consultant and obtain approval
Submit and obtain approval for Laydown Area plan with details.
Stamp Construction Drawings and Documents
Prepare and maintain Drawing Control logs
Planning Requirements
Submit Baseline Program with Material Procurement Schedule
Labour Histograms to Consultant for approval.
QA/QC Requirements
Prepare and Submit the Project Specific Quality Plan
Obtain approval of the Project Specific Quality Plan
Prepare and Submit the General Method Statement
HSE Requirements
Obtain Approval for Project Specific HSE Plan.
Ensure latest & applicable HSE legislation are available at Site
Site Stores
Set up Site Stores
Construction Plant, Tools, and Equipment
Obtain the necessary road permits/security passes for vehicles involved in mobilization.
Obtain the equipment required for the mobilization
Setup workshop facility for minor repairs on site or arrange external service
Erect Construction Aids (Temporary Cranes, Temporary Hoists, Temporary Scaffolding, and Platforms)